## Sheet1
BASED on
|  |  |  | Quantity | [9 empty] | 20 wk LEAD TIME
In Current Production: | Board Description | Approval Date | Ampacity | Swbds | Sections | Engineer | DIFFICULTY | DESIGN START | Design Completed | # Design Days | Production START | Production Completed | # Production Days | Due on Site | NOTES
601 Lafayette (24-028):
- HSW1 (Sections 1-6)
- HSW2 (Sections 1-4)
Waldorf Astoria Miami (24-005):
- V.MSBH (Sections 1-2)
- GDP (Sections 1-5)
- R/MSBH (Section 1)
Paseo South Gulch Tower 2 (25-054):
- MC-14 (Section 1)
- MC-22 (Section 1)
Finishing Design Completion:
710 Edge (24-012):
MHSB (Sections 1-3) | [5 empty] | Emmanuel |  | 2025-09-10 | [6 empty] | ETA start 9/26/25
MCSB-1 (Section 1) | [5 empty] | Emmanuel |  | 2025-09-10 | [6 empty] | ETA start 9/26/26
MCSB-2 (Section 1) | [5 empty] | Emmanuel |  | 2025-09-10 | [6 empty] | ETA start 9/26/27
Four Seasons – Las Vegas (24-088):
- N-MSBHA (Sections 1-3) | [5 empty] | Emmanuel |  | 2025-08-25
- N-GSBHA (Sections 1-3) | [5 empty] | Emmanuel |  | 2025-08-25 |  |  | 2025-09-23
- S-MSBHA (Sections 1-3) | [5 empty] | Emmanuel |  | 2025-08-25
- S-GSBHA (Sections 1-4) | [5 empty] | Emmanuel |  | 2025-08-25 |  |  | 2025-09-23
- C-MSBHA (Sections 1-4) | [5 empty] | Emmanuel |  | 2025-08-25 |  |  | 2025-09-23
- C-GSBHA (Sections 1-4) | [5 empty] | Emmanuel |  | 2025-08-25 |  |  | 2025-09-23
Henry Tower One (25-051):
SB-RES-LW (Sections 1-2) | [5 empty] | Shannon |  | 2025-08-21 | 2025-09-10 | 20
SB-RES-UW (Sections 1-2) |  |  |  | 1 | 2 | Niel |  | 2025-08-20 | 2025-09-01 | 12
SB-RES-UE (Sections 1-2) |  |  |  | 1 | 2 | Niel |  | 2025-08-18 | 2025-09-01 | 14
SB-RES-LE (Sections 1-2) |  |  |  | 1 | 2 | Niel |  | 2025-08-27 | 2025-09-01 | 5
LL2-BSWBD-1 (Sections 1-5) | [5 empty] | Emmanuel |  | 2025-08-29 |  | -45898 | 2025-09-25
Culpepper at TAMU (25-135):
MSBR-N (Sections 1-2) |  |  |  | 1 | 2 | Neil |  | 2025-09-08 | 2025-09-09 | 1
MSBR-S (Sections 1-2) |  |  |  | 1 | 2 | Neil |  | 2025-08-28 | 2025-09-08 | 11
MSBH (Sections 1-4) |  |  |  | 1 | 4 | Neil |  | 2025-09-12 | 2025-09-19 | 7 | 2025-09-22
Gasworx E3 (25-050):
MSBH1A (Sections 1-2) | 2000a Pull Section and dist. Section |  |  | 1 | 2 | Shannon | Easy | 2025-09-18 | [6 empty] | 5 Days for this design
MSBH1B (Sections 1-2) | 2000a Pull Section and dist. Section |  |  | 1 | 2 | Shannon | Easy | 2025-09-24
MSBL1(Sections 1-2) | 2000a Pull Section and dist. Section |  |  | 1 | 2 | Neil | Easy | 2025-09-20
MSBL2 (Sections 1-2) | 2000a Pull Section 2000a MCB |  |  | 1 | 2 | Neil | Easy | 2025-09-24
MSBL3 (Sections 1-3) | 2000a Pull Section 2000a MCB |  |  | 1 | 3 | Neil | Easy | 2025-09-29
Island of Westbay (25-181):
MSBA (Sections 1-2) |  |  |  | 1 | 2 | Shannon |  | 2025-09-29
MSBH (Sections 1-3) |  |  |  | 1 | 3 | Neil
MSBE (Sections 1-2) |  |  |  | 1 | 2 | Shannon
Catawba College (25-179):
MDS (Sections 1-2) | [10 empty] | 2025-09-23
The Edge Sarasota (25-027):
OSDP (Section 1) | [5 empty] | Shannon |  | 2025-08-29 |  |  | 2025-09-18
R1 (Section 1) | [5 empty] | Shannon |  | 2025-08-29 |  |  | 2025-09-18
Phillips Point (25-098):
HSB-7 (Section 1) | 1600a Bus Distribution Section |  | 1600 | 1 | 1 | Jacob Jagger | EASY | 2025-09-05 | 2025-09-12 | 7 | 2025-09-12 |  |  |  | Prioritize BUILD
TSB-1 (Sections 1-5) | 4000a bus 4000a MCB Bus In Top |  | 4000 | 1 | 5 | Emmanuel | Medium |  |  | 0
HSB-1 (Section 1) | 1600a Bus Distribution Section |  | 1600 | 1 | 1 | Neil | EASY | 2025-09-19 | 2025-09-21 | 2
MSB-TEMP (Sections 1-2) | 4000a bus 4000a MCB Bus In Top REAR |  | 4000 | 1 | 2 | Jacob Jagger | EASY |  |  | 0
EMSB-7 (Sections 1-6) | 4000a bus 2000a MCB Cable In Top |  | 2000 | 1 | 6 | Jacob Jagger | Medium | 2025-09-12 | 2025-10-03 | 21
MSB-1 (Sections 1-5) | 4000a bus 4000a MCB Bus In Top |  | 4000 | 1 | 5 | Jacob Jagger | HARD
Cherry Lane (fka Cherry Creek) Replacement Board | [5 empty] | Emmanuel |  | 2025-09-25
Optima
250 Church (fka 201 Boyett)
The Creamery
Santander Tower
Bentley
ONE PARK QUAY |  | 2025-09-24
MSSB-A | (3) section 3000a bus 3000a MCB Stab Fed Bottom |  | 3000 | 1 | 3 |  | Easy
MSSB-B | (3) section 2000a bus 2000a MCB Stab Fed Bottom |  | 2000 | 1 | 3 |  | Easy
MSSB-C | (3) section 2500a bus MLO Stab Fed Bottom |  | 2500 | 1 | 3 |  | Easy
HDSB | (3) section 2000a bus 2000a MCB Stab Fed Bottom |  | 2000 | 1 | 3 |  | Easy