## Sheet1
Board | Project Name | Job # | Equipment | Description | QTY | Amps | LFG ENG | Design Start Date | Design End Date | # Design Days | Difficulty | Quarter
SWBD MDS New Residence Hall (fka Catawba College) | New Residence Hall (fka Catawba College) | SM25-179 | SWBD MDS |  | 2 | 1600 | Neil | 2025-08-07 | 2025-08-19 | 12 | Easy | 2025Q3
SB-RES-UE The Henry Tower One | The Henry Tower One | SM25-051 | SB-RES-UE |  | 2 | 2500 | Neil | 2025-08-18 | 2025-09-01 | 14 | Easy | 2025Q3
SB-RES-UW The Henry Tower One | The Henry Tower One | SM25-051 | SB-RES-UW |  | 2 | 3000 | Neil | 2025-08-20 | 2025-09-01 | 12 | Easy | 2025Q3
SB-RES-LW The Henry Tower One | The Henry Tower One | SM25-051 | SB-RES-LW |  | 2 | 4000 | Shannon | 2025-08-21 | 2025-09-10 | 20 | Easy | 2025Q3
SB-RES-LE The Henry Tower One | The Henry Tower One | SM25-051 | SB-RES-LE |  | 2 | 3000 | Neil | 2025-08-27 | 2025-09-01 | 5 | Easy | 2025Q3
MSBR-N Culpepper at TAMU | Culpepper at TAMU | SM25-135 | MSBR-N | 120/208V 3PH 4W 4000a LSIG MCB 65 KAIC NEMA 1 | 2 | 4000 | Neil | 2025-08-28 | 2025-09-08 | 11 | Med | 2025Q3
HSB-7 Phillips Point Arcade (SOS) | Phillips Point Arcade (SOS) | SM25-098 | HSB-7 | 3ph 4W 277/480v 1600a MLO 65 KAIC | 1 | 1600 | Jacob | 2025-09-05 | 2025-09-12 | 7 | Easy | 2025Q3
MSBR-S Culpepper at TAMU | Culpepper at TAMU | SM25-135 | MSBR-S | 120/208V 3PH 4W 3500a LSIG MCB 65 KAIC NEMA 1 | 2 | 3500 | Neil | 2025-09-08 | 2025-09-09 | 1 | Med | 2025Q3
MSBH Culpepper at TAMU | Culpepper at TAMU | SM25-135 | MSBH | 277/480v 3PH 4W 3000a LSIG MCB 65 KAIC NEMA 1 | 4 | 3000 | Neil | 2025-09-12 | 2025-09-19 | 7 | Med | 2025Q3
EMSB-7 Phillips Point Arcade (SOS) | Phillips Point Arcade (SOS) | SM25-098 | EMSB-7 | (7) Section 3ph 4W 277/480v 4000a MLO 65 KAIC | 6 | 4000 | Jacob | 2025-09-12 | 2025-10-07 | 25 | Med | 2025Q3
MSBH1A Gasworx - South Ybor E3 | Gasworx - South Ybor E3 | SM25-050 | MSBH1A | 277/480v 3PH 4W 2000a MLO 65 KAIC NEMA 1 | 2 | 2000 | Shannon | 2025-09-18 | 2025-10-03 | 15 | Easy | 2025Q3
HSB-1 Phillips Point Arcade (SOS) | Phillips Point Arcade (SOS) | SM25-098 | HSB-1 | (3) Section 3ph 4W 277/480v 1600a MLO 65 KAIC | 1 | 1600 | Neil | 2025-09-19 | 2025-09-21 | 2 | Easy | 2025Q3
MSBL1 Gasworx - South Ybor E3 | Gasworx - South Ybor E3 | SM25-050 | MSBL1 | 120/208v 3PH 4W 2500a MLO 65 KAIC NEMA 1 | 2 | 2500 | Neil | 2025-09-24 | 2025-09-29 | 5 | Easy | 2025Q3
TSB-1 Phillips Point Arcade (SOS) | Phillips Point Arcade (SOS) | SM25-098 | TSB-1 | (6) section 3ph 4W 277/480v 4000a GFP MCB 65 KAIC | 5 | 4000 | Emma | 2025-09-26 | 2025-12-18 | 83 | Med | 2025Q3
MSBL2 Gasworx - South Ybor E3 | Gasworx - South Ybor E3 | SM25-050 | MSBL2 | 120/208v 3PH 4W 2500a MLO 65 KAIC NEMA 1 | 2 | 2500 | Neil | 2025-09-29 | 2025-10-01 | 2 | Easy | 2025Q3
MSB-1 Phillips Point Arcade (SOS) | Phillips Point Arcade (SOS) | SM25-098 | MSB-1 | (5) Section 3ph 4W 277/480v 4000a MCB 65 KAIC | 5 | 4000 | Emma | 2025-10-02 | 2025-12-15 | 74 | Hard | 2025Q4
MSBH1B Gasworx - South Ybor E3 | Gasworx - South Ybor E3 | SM25-050 | MSBH1B | 277/480v 3PH 4W 2000a MLO 65 KAIC NEMA 1 | 2 | 2000 | Shannon | 2025-10-06 | 2025-10-16 | 10 | Easy | 2025Q4
MSB2-HA Replacement Board Cherry Lane (fka West Clayton) | Cherry Lane (fka West Clayton) | SM25-225 | MSB2-HA Replacement Board | Bus 2000a MCB Bottom Fed Cable | 4 | 2000 | Emma | 2025-10-07 | 2025-10-10 | 3 | Med | 2025Q4
MSBL3 Gasworx - South Ybor E3 | Gasworx - South Ybor E3 | SM25-050 | MSBL3 | 120/208v 3PH 4W 2500a MLO 65 KAIC NEMA 1 | 3 | 4000 | Neil | 2025-10-08 | 2025-10-14 | 6 | Easy | 2025Q4
LL2-BSWBD-1 The Henry Tower One | The Henry Tower One | SM25-051 | LL2-BSWBD-1 |  | 5 | 4000 | Neil | 2025-10-14 | 2025-10-22 | 8 | Med | 2025Q4
RMDP The Creamery - Phase I | The Creamery - Phase I | SM25-079 | RMDP | 277/480v 3ph 4w 2000a MCB 65 KAIC NEMA 1 | 3 | 2000 | Shannon | 2025-10-17 | 2025-11-05 | 19 | Easy | 2025Q4
MCSB1 710 Edge (aka Villa Miami) | 710 Edge (aka Villa Miami) | SM24-012 | MCSB1 |  | 1 | 2500 | Emma | 2025-10-22 | 2025-10-24 | 2 | Easy | 2025Q4
MCSB2 710 Edge (aka Villa Miami) | 710 Edge (aka Villa Miami) | SM24-012 | MCSB2 |  | 1 | 2500 | Emma | 2025-10-22 | 2025-10-24 | 2 | Easy | 2025Q4
MSBA The Island at West Bay Club | The Island at West Bay Club | SM25-181 | MSBA | 120/208v 3PH 4W 4000a BUS 4000A MCB 65 KAIC NEMA 1 | 2 | 4000 | Neil | 2025-10-22 | 2025-10-28 | 6 | Easy | 2025Q4
MSHB 710 Edge (aka Villa Miami) | 710 Edge (aka Villa Miami) | SM24-012 | MSHB |  | 3 | 2500 | Emma | 2025-10-24 | 2025-11-05 | 12 | Med | 2025Q4
MSBR 250 Church Ave (fka 201 Boyett) | 250 Church Ave (fka 201 Boyett) | SM25-205 | MSBR | 120/208v 3PH 4W 4000a BUS 4000a ARMS MCB 65 KAIC NEMA 1 | 2 | 4000 | Jacob | 2025-10-27 | 2025-11-06 | 10 | Easy | 2025Q4
MSBH The Island at West Bay Club | The Island at West Bay Club | SM25-181 | MSBH | 120/208v 3PH 4W 4000a BUS 4000A MCB 65 KAIC NEMA | 3 | 4000 | Neil | 2025-10-28 | 2025-11-05 | 8 | Easy | 2025Q4
MSBE The Island at West Bay Club | The Island at West Bay Club | SM25-181 | MSBE | 120/208v 3PH 4W 2000a BUS 2000A MCB 65 KAIC NEMA | 2 | 2000 | Neil | 2025-10-28 | 2025-11-05 | 8 | Easy | 2025Q4
RMSB1 Shell Bay Tower 200 | Shell Bay Tower 200 | SM25-082 | RMSB1 | 120/208v 3PH 4W 2000a MCB 65 KAIC NEMA 1 | 1 | 2000 | Emma | 2025-11-05 | 2025-11-11 | 6 | Easy | 2025Q4
MSBH 250 Church Ave (fka 201 Boyett) | 250 Church Ave (fka 201 Boyett) | SM25-205 | MSBH | 277/480v 3PH 4W 2000a BUS 2000a GFP MCB 65 KAIC NEMA 1 | 3 | 1600 | Neil | 2025-11-05 | 2025-11-12 | 7 | Easy | 2025Q4
R2 The Creamery - Phase I | The Creamery - Phase I | SM25-079 | R2 | 120/208V 3PH 4W 3000A MCB 65 KAIC NEMA 1 | 2 | 3000 | Shannon | 2025-11-05 | 2025-11-19 | 14 | Easy | 2025Q4
RMSB2 Shell Bay Tower 200 | Shell Bay Tower 200 | SM25-082 | RMSB2 | 120/208v 3PH 4W 2000a MCB 65 KAIC NEMA 1 | 1 | 2000 | Emma | 2025-11-11 | 2025-11-12 | 1 | Easy | 2025Q4
HMSB Shell Bay Tower 200 | Shell Bay Tower 200 | SM25-082 | HMSB | 277/480v 3PH 4W 4000a MCB 65 KAIC NEMA 1 | 4 | 4000 | Emma | 2025-11-12 | 2025-11-14 | 2 | Med | 2025Q4
R1 The Creamery - Phase I | The Creamery - Phase I | SM25-079 | R1 | 120/208V 3PH 4W 3000A MCB 65 KAIC NEMA 1 | 2 | 3000 | Shannon | 2025-11-13 | 2025-12-02 | 19 | Easy | 2025Q4
RH West Eleventh | West Eleventh | SM25-130 | RH | 120/208V 3PH 4W 4000a MCB 100 KAIC NEMA 1 | 1 | 1600 | Neil | 2025-11-14 | 2025-11-18 | 4 | Easy | 2025Q4
MSSB-A One Park (Quay Block 1) | One Park (Quay Block 1) | SM25-127 | MSSB-A | 120/208v 3PH 4W 4000a BUS MLO 100 KAIC NEMA 1 | 3 | 3000 | Emma | 2025-11-17 | 2025-12-03 | 16 | Easy | 2025Q4
MSBR West Eleventh | West Eleventh | SM25-130 | MSBR | 120/208V 3PH 4W 3000a MCB 100 KAIC NEMA 1 | 1 | 1200 | Neil | 2025-11-18 | 2025-11-20 | 2 | Med | 2025Q4
MSBH West Eleventh | West Eleventh | SM25-130 | MSBH | 120/208V 3PH 4W 3000a MCB 100 KAIC NEMA 1 | 3 | 3000 | Neil | 2025-11-20 | 2026-01-12 | 53 | Med | 2025Q4
MSBV West Eleventh | West Eleventh | SM25-130 | MSBV | 120/208V 3PH 4W 2000a MCB 100 KAIC NEMA 1 | 2 | 1200 | Neil | 2025-12-03 | 2025-12-08 | 5 | Med | 2025Q4
MSSB-B One Park (Quay Block 1) | One Park (Quay Block 1) | SM25-127 | MSSB-B | 120/208v 3PH 4W 3000a BUS 2000a MCB 100 KAIC NEMA 1 | 4 | 2000 | Emma | 2025-12-03 | 2025-12-10 | 7 | Easy | 2025Q4
3RE Optima OMMV 7230 - Building 3 | Optima OMMV 7230 - Building 3 | SM25-086 | 3RE | 120/208V 3PH 4W 2500a MCB 65 KAIC NEMA 1 | 2 | 2500 | Shannon | 2025-12-03 | 2025-12-10 | 7 | Easy | 2025Q4
3RW Optima OMMV 7230 - Building 3 | Optima OMMV 7230 - Building 3 | SM25-086 | 3RW | 120/208V 3PH 4W 2000a MCB 65 KAIC NEMA 1 | 2 | 2000 | Shannon | 2025-12-10 | 2025-12-15 | 5 | Easy | 2025Q4
MSSB-C One Park (Quay Block 1) | One Park (Quay Block 1) | SM25-127 | MSSB-C | 480/277V 3PH 4W 2500a BUS MLO 100 KAIC NEMA 1 | 3 | 2500 | Emma | 2025-12-10 | 2025-12-23 | 13 | Easy | 2025Q4
3H Optima OMMV 7230 - Building 3 | Optima OMMV 7230 - Building 3 | SM25-086 | 3H | 480/277V 3PH 4W 3000a MCB 65 KAIC NEMA 1 | 5 | 3000 | Shannon | 2025-12-15 | 2025-12-24 | 9 | Hard | 2025Q4
MSA Cedar Park Hotel | Cedar Park Hotel | SM25-226 | MSA | 277/480v 3PH 4W 4000a BUS 4000a ARMS MCB 100 KAIC NEMA 1 | 5 | 4000 | Neil | 2025-12-19 | 2025-12-30 | 11 | Med | 2025Q4
HDSB One Park (Quay Block 1) | One Park (Quay Block 1) | SM25-127 | HDSB | 480/277V 3PH 4W 1600a MCB 100 KAIC NEMA 1 | 3 | 2000 | Emma | 2025-12-23 | 2025-12-29 | 6 | Easy | 2025Q4
DHC Cedar Park Conference Center | Cedar Park Conference Center | SM25-226 | DHC | 277/480v 3PH 4W 1600a BUS 1600a MLO 65 KAIC NEMA 1 | 1 | 1600 | Neil | 2026-01-02 | 2026-01-05 | 3 | Easy | 2026Q1
SB2 Winsupply Craddock | Winsupply Craddock | SM25-265 | SB2 | 277/480v 3PH 4W 2000a AL BUS 2000a ARMS MCB 65 KAIC NEMA 1 | 2 | 2000 | Emma | 2026-01-05 | 2026-01-14 | 9 | Easy | 2026Q1
DLC Cedar Park Conference Center | Cedar Park Conference Center | SM25-226 | DLC | 120/208v 3PH 4W 1600a BUS 1600a ARMS MCB 65 KAIC NEMA 1 | 2 | 1600 | Neil | 2026-01-06 | 2026-01-12 | 6 | Easy | 2026Q1
A1HSW TCU Housing - Parcel A, B, and C | TCU Housing - Parcel A, B, and C | SM25-206 | A1HSW | 277/480v 3PH 4W 3000a ARMS MCB 65 KAIC NEMA 1 | 2 | 3000 | Neil | 2026-01-13 | 2026-01-16 | 3 | Easy | 2026Q1
MSB4AR Hub Knoxville - Building 4 | Hub Knoxville - Building 4 | SM25-204 | MSB4AR | 120/208v 3PH 4W 3500a ARMS MCB 100 KAIC NEMA 1 | 5 | 3500 | Emma | 2026-01-16 | 2026-01-23 | 7 | Med | 2026Q1
Amenity Hub Tampa Phase 2 | Hub Tampa Phase 2 | SM24-014 | Amenity | 120/208v 3PH 4W 2000a MCB 65 KAIC NEMA 1 | 2 | 2000 | Shannon | 2026-01-20 | 2026-01-26 | 6 | Easy | 2026Q1
MSB-Temp Phillips Point Arcade (SOS) | Phillips Point Arcade (SOS) | SM25-098 | MSB-Temp | (2) Section 3ph 4W 277/480v 4000a LSIG MCB | 2 | 4000 | Neil | 2026-01-21 | 2026-01-26 | 5 | Easy | 2026Q1
MSB COTA - Circuit of the Americas | COTA - Circuit of the Americas | SM26-0008 | MSB |  | 2 | 2000 | Emma | 2026-01-23 | 2026-01-24 | 1 | Easy | 2026Q1
PKDP + SPD Hub Tampa Phase 2 | Hub Tampa Phase 2 | SM25-180 | PKDP + SPD | 120/208v 3PH 4W 2000A MCB 65 KAIC NEMA 1 | 2 | 2000 | Shannon | 2026-01-26 | 2026-01-29 | 3 | Easy | 2026Q1
MSB4BR Hub Knoxville - Building 4 | Hub Knoxville - Building 4 | SM25-204 | MSB4BR | 120/208v 3PH 4W 2500a ARMS MCB 100 KAIC NEMA 1 | 4 | 2500 | Emma | 2026-01-27 | 2026-01-29 | 2 | Easy | 2026Q1
MSB4BH Hub Knoxville - Building 4 | Hub Knoxville - Building 4 | SM25-204 | MSB4BH | 120/208v 3PH 4W 2000a ARMS MCB 100 KAIC NEMA 1 | 4 | 2000 | Emma | 2026-01-30 | 2026-02-13 | 14 | Easy | 2026Q1
MSB - BLDG E Ivy Corridor | Ivy Corridor | SM25-255 | MSB - BLDG E |  | 3 | 1600 | Neil | 2026-02-05 | 2026-02-13 | 8 | Med | 2026Q1
Legally Required Generator Main St Regis Residences Brickell (fka 1809 Brickell Ave) | St Regis Residences Brickell (fka 1809 Brickell Ave) | SM25-133 | Legally Required Generator Main |  | 1 | 1600 | Shannon | 2026-02-10 | 2026-02-16 | 6 | Easy | 2026Q1
MSB4AH Hub Knoxville - Building 4 | Hub Knoxville - Building 4 | SM25-204 | MSB4AH | 120/208v 3PH 4W 2000a ARMS MCB 100 KAIC NEMA 1 | 4 | 2500 | Emma | 2026-02-10 | 2026-02-17 | 7 | Med | 2026Q1
Legally Required Main St Regis Residences Brickell (fka 1809 Brickell Ave) | St Regis Residences Brickell (fka 1809 Brickell Ave) | SM25-133 | Legally Required Main | 480/277V 3PH 4W 1600a MCB 100 KAIC NEMA 1 | 1 | 1600 | Shannon | 2026-02-16 | 2026-02-19 | 3 | Easy | 2026Q1
MSB - BLDG F Ivy Corridor | Ivy Corridor | SM25-255 | MSB - BLDG F |  | 3 | 3000 | Neil | 2026-02-16 | 2026-02-24 | 8 | Med | 2026Q1
SWBD Main 2 St Regis Residences Brickell (fka 1809 Brickell Ave) | St Regis Residences Brickell (fka 1809 Brickell Ave) | SM25-133 | SWBD Main 2 | 120/208V 3PH 4W 3000a MCB 100 KAIC NEMA 1 | 1 | 3000 | Shannon | 2026-02-16 | 2026-03-02 | 14 | Easy | 2026Q1
SWBD Main 3 St Regis Residences Brickell (fka 1809 Brickell Ave) | St Regis Residences Brickell (fka 1809 Brickell Ave) | SM25-133 | SWBD Main 3 | 120/208V 3PH 4W 3000a MCB 100 KAIC NEMA 1 | 1 | 3000 | Shannon | 2026-02-16 | 2026-03-02 | 14 | Easy | 2026Q1
MAIN #1 320 Lakeview Ave | 320 Lakeview Ave | SM25-203 | MAIN #1 | 120/208V 3PH 4W 2000a BUS 2000a ARMS LSIG MCB 65 KAIC | 1 | 2000 | Neil | 2026-02-23 | 2026-02-25 | 2 | Easy | 2026Q1
MAIN #2 320 Lakeview Ave | 320 Lakeview Ave | SM25-203 | MAIN #2 | 120/208 3PH 4W 2000a BUS 2000a ARMS LSIG MCB 65 KAIC | 1 | 2000 | Neil | 2026-02-23 | 2026-02-25 | 2 | Easy | 2026Q1
MAIN #3 320 Lakeview Ave | 320 Lakeview Ave | SM25-203 | MAIN #3 | 277/480v 3PH 4W 3000a BUS 3000a ARMS LSIG MCB 65 KAIC | 1 | 3000 | Neil | 2026-02-26 |  |  | Easy | 2026Q1
SWBD Main 1 St Regis Residences Brickell (fka 1809 Brickell Ave) | St Regis Residences Brickell (fka 1809 Brickell Ave) | SM25-245 | SWBD Main 1 | 120/208V 3PH 4W 4000a MCB 100 KAIC NEMA 1 | 2 | 4000 | Shannon | 2026-03-03 | 2026-03-16 | 13 | Easy | 2026Q1
NMSBH Ritz Carlton Res Bay P2 | Ritz Carlton Res Bay P2 | SM25-210 | NMSBH | 277/480v 3PH 4W 3000a BUS 3000a ARMS MCB 65 KAIC NEMA 1 | 3 | 3000 | Neil | 2026-03-10 | 2026-03-16 | 6 | Easy | 2026Q1
HDP Main 4 St Regis Residences Brickell (fka 1809 Brickell Ave) | St Regis Residences Brickell (fka 1809 Brickell Ave) | SM25-133 | HDP Main 4 | 480/277V 3PH 4W 4000a MCB 100 KAIC NEMA 1 | 3 | 4000 | Shannon | 2026-03-16 | 2026-03-17 | 1 | Med | 2026Q1
EQMH Bentley Residences | Bentley Residences | SM25-191 | EQMH | 480/277v 3ph 4w 1600a MLO 65KAIC NEMA 3R | 2 | 1600 | Micah | 2026-03-16 | 2026-03-20 | 4 | Easy | 2026Q1
NMSBE Ritz Carlton Res Bay P2 | Ritz Carlton Res Bay P2 | SM25-210 | NMSBE | 277/480v 3PH 4W 1600a BUS 1600a GFP MCB 65 KAIC NEMA 1 | 3 | 1600 | Neil | 2026-03-17 | 2026-03-23 | 6 | Easy | 2026Q1
Car Charge Main 1 St Regis Residences Brickell (fka 1809 Brickell Ave) | St Regis Residences Brickell (fka 1809 Brickell Ave) | SM25-133 | Car Charge Main 1 | 120/208V 3PH 4W 2000a MCB 100 KAIC NEMA 1 | 2 | 2000 | Shannon | 2026-03-18 | 2026-03-24 | 6 | Easy | 2026Q1
EMOP Bentley Residences | Bentley Residences | SM25-131.01 | EMOP | 120/208v 3PH 4W 2000a MLO 65 KAIC NEMA 1 | 2 | 2000 | Micah | 2026-03-20 | 2026-03-23 | 3 | Easy | 2026Q1